## Sheet1
DocType_REV_ID | Entry Date | Review by | Detection version | Page/Line/Section/Entity | Open point: description of problem | Proposed Solution | Status
CR_REV_0001 | 2022-02-11 | Salma Saeed | V1.0 | 1/Document History: | All edits shall be in document history | Add edits of System Context | Closed
CR_REV_0002 | 2022-02-11 | Salma Saeed | V1.0 | 2/System Context: | format of System Context | format shall be bigger and more organized | Closed
CR_REV_0003 | 2022-02-11 | Salma Saeed | V1.0 | 3/CRS Requirements:Req_1 | The way of writing is not formal | Description must be more descriptive and formal | Closed
CR_REV_0004 | 2022-02-11 | Salma Saeed | V1.0 | 3/CRS Requirements:Req_2 | this Requirement is more software | shall be removed | Closed
CR_REV_0005 | 2022-02-11 | Salma Saeed | V1.0 | 3/CRS Requirements:Req_4 | this Requirement is not part of real time execution | shall be removed | Closed
CR_REV_0006 | 19/11 | Salma Saeed | V1.0 | Document Status: Status | wrong status | shall be proposed | Closed
CR_REV_0007 | 19/11 | Salma Saeed | V1.0 | 2/System Context: | edit system context | shall have two blocks :bump detection class , ECU and edit input and output signals | Closed
CR_REV_0008 | 19/11 | Salma Saeed | V1.0 | 3/CRS Requirements | Edit CRS Requirements | CRS Requirements shall have more detials | Closed